YAT  COLLEGE

YAT College  ·  175 Cremorne St, Cremorne VIC 3121

# Business Case

YAT LMS Replacement — GrayBoard to DOODLE

| Prepared for | YAT Board, via Sam Walker (YAT ICT Manager) |
| --- | --- |
| Prepared by | AccentLoitte Consulting |
| Reviewed by | Jamie O'Donnell, AccentLoitte Senior Consultant |
| Engagement | YAT LMS Replacement Project — Phase 1 |
| Document version | v1.0 — Approved |
| Date | May 2022 |
| Analysis period | 5 years |
| Currency | AUD, exclusive of GST (2022 price levels) |
| Classification | Commercial-in-confidence |

# Contents

Contents	2

1. Executive Summary	3

2. Strategic Alignment Analysis	3

3. Current State — the GrayBoard LMS	3

4. Gap Analysis	4

5. Options Considered and Evaluation	4

5.1 Workload definition	4

5.2 Options considered	4

5.3 Evaluation method	4

5.4 Initial impact and difficulty assessment	5

6. Cost-Benefit Analysis	5

6.1 Assumptions	5

6.2 Option A — 5-year summary	5

6.3 Option B — 5-year summary	6

6.4 Quantified benefit — avoided downtime	6

6.5 Comparison summary	6

7. Risk and Impact Assessment	6

7.1 Intangibles comparison	6

7.2 Risk register (recommended option)	7

8. Recommendation	7

9. Action Plan	7

9.1 Prioritised changes	7

9.2 Implementation schedule	7

9.3 Standards, targets, and success metrics	8

9.4 Implementation methods	8

9.5 Alignment with change-management procedure	8

10. Next Steps and Decision Requested	8

11. Feedback	8

Sign-off	9

Appendix 1 — Cost Detail	10

A1.1 Option A — Remediate and retain GrayBoard	10

A1.2 Option B — Replace with DOODLE (on-premises)	10

Appendix 2 — LMS Market Evaluation (summary)	11

# 1. Executive Summary

YAT's Learning Management System, GrayBoard, is a bespoke in-house platform that has reached end of supportable life. Its availability and performance have been degrading, it has no vendor support or product roadmap, and it does not meet current accessibility obligations — placing YAT's teaching delivery and compliance at growing risk. This Business Case evaluates two options over a five-year horizon: Option A — remediate and retain GrayBoard; Option B — replace it with a supported contemporary LMS (DOODLE) deployed on-premises at the Cremorne campus.

Option A is ~$63,600 cheaper over five years on direct cost, but it only defers the problem: it leaves YAT on an unsupported, dead-end platform with a heavy in-house maintenance burden and a fragile accessibility retrofit, and a full replacement would still be required. Option B delivers a vendor-supported, WCAG 2.1 AA-compliant, performant LMS with an active product roadmap, preserves all student records, and actually reduces YAT's ongoing maintenance burden — partly offsetting the higher upfront cost.

We recommend Option B. We ask the board to approve the replacement, the phased implementation plan in §9 (with cutover scheduled into the December–January teaching break), and the Year-1 budget envelope.

# 2. Strategic Alignment Analysis

YAT's ICT direction in 2022 prioritises reliable, well-supported core systems; the capacity to support continued student growth; and meeting the College's statutory obligations as a Registered Training Organisation. The LMS is the platform through which teaching, assessment and student records are delivered and held, so its reliability and compliance are foundational to that direction.

Across the RTO sector, institutions have moved decisively off bespoke in-house LMS platforms onto established, vendor-supported products with active communities and accessibility conformance — driven by the maintenance cost and compliance risk of home-grown systems, and by rising accessibility expectations under the Disability Discrimination Act 1992. YAT's continued reliance on GrayBoard runs against this direction. Cloud-hosted delivery is the emerging next step in the sector; YAT notes it as a future consideration but, consistent with its then-current on-premises operating model, this engagement is scoped to an on-premises replacement. Replacing GrayBoard now with a supported product both resolves the immediate risk and positions YAT for a future move to cloud hosting.

# 3. Current State — the GrayBoard LMS

GrayBoard is a bespoke LMS built and maintained in-house by YAT ICT, running on on-premises infrastructure at the Cremorne campus and integrated with Active Directory (authentication), Office 365 (email notifications), and AVETMISS/ASQA statutory reporting. It has reached end of supportable life: effective availability has been degrading, typical and peak-load performance is declining (the platform struggles with the ~3× concurrent load during end-of-term assessment windows), and it depends on a small number of YAT staff for continued maintenance with no external support or product roadmap. It does not meet WCAG 2.1 Level AA, creating a compliance exposure under the Disability Discrimination Act. It does, however, hold YAT's complete student-record history, which carries long-tail retention obligations under the Standards for RTOs 2015 — so any replacement must preserve those records with full integrity. These limitations — no support, declining availability and performance, accessibility non-conformance, and concentration risk on in-house maintenance — are what drive the gap analysis.

# 4. Gap Analysis

| Strategic objective | Current state (GrayBoard) | Gap | Improvement opportunity | Proposed change |
| --- | --- | --- | --- | --- |
| Supported, current LMS platform | Bespoke, end-of-life, no vendor support/roadmap | No support or roadmap; concentration risk | Adopt an established commercial LMS | Replace with DOODLE (on-prem) |
| Availability ≥ 99% | Degrading, below target | Reliability shortfall | Modern supported stack | Deploy DOODLE on supported infrastructure |
| WCAG 2.1 AA accessibility | Non-conformant (DDA exposure) | Compliance gap | Product with native AA conformance | Replace with conformant LMS |
| Peak-load performance | Degrades at ~3× term-end load | Performance shortfall | Right-sized supported platform | Provision DOODLE to peak profile |
| Preserve all student records | Held in GrayBoard | Migration risk if not managed | Verified ETL migration | Migrate with reconciliation + parallel run |

The gaps cluster around supportability, reliability, compliance and performance — none of which an in-house remediation truly closes, and all of which a supported replacement addresses while also preserving the student-record history.

# 5. Options Considered and Evaluation

## 5.1 Workload definition

The replacement must: be a current, vendor-supported LMS product; run on YAT's Windows Server 2016 on-premises hosting standard; preserve all GrayBoard student records with full integrity; achieve ≥ 99% availability; meet WCAG 2.1 AA; match or exceed GrayBoard's performance (including ~3× term-end peaks); integrate with Active Directory, Office 365 and AVETMISS reporting; and carry vendor support with severity-1 response within 4 hours during teaching hours.

## 5.2 Options considered

Option A — Remediate and retain GrayBoard: invest in an accessibility retrofit and a hardware refresh, and continue in-house maintenance of the legacy platform.

Option B — Replace with a contemporary on-prem LMS (DOODLE): select an established product via market evaluation (see Appendix 2), deploy it on YAT infrastructure, migrate the data, and train staff.

A SaaS / cloud-hosted LMS was considered but not carried forward in this engagement: it is inconsistent with YAT's current on-premises operating model and is noted as a future option.

## 5.3 Evaluation method

Each option is evaluated with a five-year cost-benefit analysis (§6), an intangibles comparison covering support, compliance, reliability and maintenance burden (§7.1), and a risk register (§7.2). Because the decision turns largely on supportability and compliance rather than on cost alone, the intangibles carry significant weight.

## 5.4 Initial impact and difficulty assessment

|  | Option A — Remediate GrayBoard | Option B — Replace (DOODLE) |
| --- | --- | --- |
| Strategic impact | Defers the problem; remains a dead-end platform | Resolves it; supported, compliant, future-ready |
| Implementation difficulty | Low — incremental work on a known system | Moderate — selection, deployment, data migration, training |
| Headline pros | Lower upfront cost; familiar platform | Vendor support + roadmap; compliant; lower ongoing maintenance |
| Headline cons | Unsupported, non-compliant, replacement still looms | Higher Year-1 cost; migration and change effort |

# 6. Cost-Benefit Analysis

A five-year cost comparison of the two options (AUD ex GST, 2022 price levels; inflation excluded for comparison clarity). Detailed line items are in Appendix 1.

## 6.1 Assumptions

| Assumption | Value | Source |
| --- | --- | --- |
| GrayBoard in-house maintenance effort | ~0.4 FTE / year | YAT ICT staffing records, FY2021–22 |
| Fully-loaded ICT staff cost | $110,000 / year | YAT Finance, 2022 salary bands |
| DOODLE licensing and vendor support | $18,400 / year | DOODLE vendor quotation, 4 March 2022 |
| GrayBoard server refresh under Option A | $55,000 one-off | YAT ICT hardware quotation, February 2022 |
| Cost of LMS downtime during teaching hours | $620 / hour | YAT Finance estimate — teaching hours lost × delivery cost, 2022 |
| Price basis | 2022 levels, AUD ex GST, inflation excluded | AccentLoitte costing convention for five-year comparisons |

Each figure is attributed so the board can see what the comparison rests on and challenge any assumption it disagrees with.

## 6.2 Option A — 5-year summary

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 5-year |
| --- | --- | --- | --- | --- | --- | --- |
| One-off remediation | $55,000 | — | — | — | — | $55,000 |
| Recurring (maintenance) | $67,000 | $67,000 | $67,000 | $67,000 | $67,000 | $335,000 |
| Annual total | $122,000 | $67,000 | $67,000 | $67,000 | $67,000 | $390,000 |

## 6.3 Option B — 5-year summary

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 5-year |
| --- | --- | --- | --- | --- | --- | --- |
| One-off project | $160,000 | — | — | — | — | $160,000 |
| Recurring (run + support) | (in project) | $73,400 | $73,400 | $73,400 | $73,400 | $293,600 |
| Annual total | $160,000 | $73,400 | $73,400 | $73,400 | $73,400 | $453,600 |

## 6.4 Quantified benefit — avoided downtime

GrayBoard's unplanned outages over FY2021–22 totalled approximately 71 hours during teaching hours. At the $620/hour cost of lost teaching delivery in §6.1, that is about $44,000 a year in disruption YAT is absorbing today. A supported platform meeting the ≥ 99% availability target would hold unplanned downtime under about 18 teaching hours a year, avoiding roughly $33,000 of that annually — some $165,000 over the five-year horizon.

This benefit is stated separately from the cost tables rather than netted off them: it is an avoided cost YAT currently absorbs across the teaching timetable, not a line item in either option's budget. Counted against the $63,600 five-year cost difference, it more than covers the gap on its own.

## 6.5 Comparison summary

|  | Option A | Option B | Delta (B − A) |
| --- | --- | --- | --- |
| One-off (Year 1) | $55,000 | $160,000 | +$105,000 |
| Recurring (per year) | $67,000 | $73,400 | +$6,400 |
| 5-year direct cost | $390,000 | $453,600 | +$63,600 |

Option B costs more on every measure — ~$105,000 more upfront and ~$6,400 more per year, ~$63,600 more over five years. The case for it is therefore not cost but supportability, compliance and performance: Option A's lower spend buys only a temporary reprieve on an unsupported, non-compliant platform that must still be replaced. Option A's cost advantage also rests on the maintenance effort assumed in §6.1 holding steady, which on this platform's trajectory it will not.

# 7. Risk and Impact Assessment

## 7.1 Intangibles comparison

| Factor | Option A — Remediate GrayBoard | Option B — Replace (DOODLE) |
| --- | --- | --- |
| Vendor support & roadmap | None — bespoke dead-end | Active vendor support + roadmap |
| Accessibility (WCAG 2.1 AA / DDA) | Fragile retrofit | Native conformance |
| Availability (≥ 99%) | Degrading | Meets target on supported stack |
| Peak-load performance | Degrades at term-end | Match/exceed; provisioned to peak |
| YAT ICT maintenance burden | High (in-house bespoke) | Reduced (supported product) |
| Future-proofing | Replacement still looms | Current platform; cloud-ready later |

## 7.2 Risk register (recommended option)

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Data loss/corruption in migration | Low | High | Verified ETL with record reconciliation; parallel run; tested backups |
| Cutover disrupts teaching | Medium | High | Cutover in the Dec–Jan break; rollback plan; staged go-live |
| Low user adoption / support spike | Medium | Medium | Role-based training before cutover; stabilisation support period |
| Integration gaps (AD / O365 / AVETMISS) | Medium | Medium | Integration testing during parallel run before cutover |
| Schedule slips into a teaching term | Low | Medium | Phase gates; the fixed Dec–Jan cutover window |

# 8. Recommendation

Recommended option: Option B — replace GrayBoard with DOODLE, deployed on-premises. Although ~$63,600 more over five years, it is the only option that delivers a supported, accessible, performant LMS with a product roadmap, reduces YAT's ongoing maintenance burden, and preserves the student-record history — while Option A merely defers an unavoidable replacement on an unsupported, non-compliant platform. This recommendation drives the phased action plan below.

# 9. Action Plan

## 9.1 Prioritised changes

| # | Phase | Priority rationale |
| --- | --- | --- |
| 1 | Selection & implementation plan | Confirm the product and the deployment/migration approach first |
| 2 | Deployment & data migration | Stand up DOODLE, migrate and verify records, run in parallel |
| 3 | Stabilisation & closure | Support, training, as-built docs, knowledge transfer, closure |

## 9.2 Implementation schedule

| Phase | Activities | Window | Dependencies | Owner |
| --- | --- | --- | --- | --- |
| 1 | Requirements, market evaluation, implementation plan | 2022 H1 | — | AccentLoitte |
| 2 | Infra provisioning, DOODLE install, ETL migration, parallel run, cutover | Dec 2022 – Jan 2023 break | Phase 1 approval | AccentLoitte + YAT ICT |
| 3 | Stabilisation support, training, as-built docs, closure pack | Jan 2023 | Phase 2 cutover | AccentLoitte + YAT ICT |

Staff training is delivered before cutover to contain the post-cutover support burden, and the cutover is scheduled into the December–January teaching break.

## 9.3 Standards, targets, and success metrics

| Aspect | Standard / target | How measured |
| --- | --- | --- |
| Availability | ≥ 99% | LMS uptime monitoring over the stabilisation period |
| Accessibility | WCAG 2.1 AA | Accessibility audit of the deployed LMS |
| Record preservation | 100% reconciliation | Post-migration record counts vs pre-migration; sample fidelity checks |
| Vendor support | Sev-1 ≤ 4h (teaching hours) | Support contract terms; incident logs |

## 9.4 Implementation methods

Deployment follows a staged method rather than a single switch. DOODLE is stood up on new infrastructure alongside the running GrayBoard platform; records are migrated by a verified ETL process with record-count reconciliation and sample fidelity checks; the two platforms then run in parallel while integrations to Active Directory, Office 365 and AVETMISS reporting are tested against live data. Cutover happens only once parallel running is clean, and GrayBoard is retained in a read-only state through the stabilisation period so there is a rollback path.

## 9.5 Alignment with change-management procedure

The cutover is a high-risk change requiring Change Advisory Board endorsement and YAT senior-management sign-off; the Phase 3 Closure Pack is signed off under the YAT Change Management Procedure.

# 10. Next Steps and Decision Requested

We ask the board to: (1) approve Option B — replacing GrayBoard with DOODLE on-premises; (2) approve the phased implementation plan in §9; and (3) authorise the Year-1 budget envelope (≈$160,000). The high-risk cutover change request is submitted at the Phase 2 gate per the change management procedure.

# 11. Feedback

Feedback received on this Business Case during review, and how each item was addressed before approval.

| From | Date | Feedback | How it was addressed |
| --- | --- | --- | --- |
| Sam Walker, YAT ICT Manager | 3 May 2022 | The five-year comparison shows Option B costing more but does not put a number on what the current outages are costing YAT. | Added §6.4 quantifying avoided downtime at ~$33,000 a year, and the $620/hour basis for it in §6.1. |
| Robin Ng, Chief Financial Officer | 9 May 2022 | Where do the staffing and licensing figures come from? | Added a Source column to the §6.1 assumptions table attributing every figure. |
| Sam Walker, YAT ICT Manager | 16 May 2022 | The plan needs to be explicit that there is a way back if cutover goes badly. | Expanded §9.4 to state the parallel-run method and the read-only GrayBoard rollback path through stabilisation. |

# Sign-off

| Role | Name | Date | Signature |
| --- | --- | --- | --- |
| Prepared by | AccentLoitte Consultant | 12 May 2022 | (signed) |
| Reviewed by | Jamie O'Donnell (AccentLoitte Senior Consultant) | 13 May 2022 | (signed) |
| Approved by | Sam Walker (YAT ICT Manager) | 20 May 2022 | (signed) |

# Appendix 1 — Cost Detail

## A1.1 Option A — Remediate and retain GrayBoard

One-off remediation (Year 1):

| Item | Cost |
| --- | --- |
| Accessibility retrofit to WCAG 2.1 AA | $35,000 |
| Legacy server hardware refresh | $20,000 |
| Total one-off | $55,000 |

Recurring (per year):

| Item | Annual cost |
| --- | --- |
| In-house bespoke maintenance (~0.4 FTE) | $44,000 |
| Incident response (~0.10 FTE, rising) | $11,000 |
| Hosting, facilities, backup | $12,000 |
| Total recurring per year | $67,000 |

## A1.2 Option B — Replace with DOODLE (on-premises)

One-off project (Year 1):

| Item | Cost |
| --- | --- |
| AccentLoitte fees (Phases 1–3: selection, deployment, migration, training, closure) | $95,000 |
| On-premises infrastructure (server, storage, UPS, backup) | $35,000 |
| YAT ICT staff time (oversight, integration, acceptance, parallel run) | $22,000 |
| Training delivery | $8,000 |
| Total Year-1 project | $160,000 |

Recurring (per year, Years 2–5):

| Item | Annual cost |
| --- | --- |
| DOODLE vendor support & maintenance contract | $30,000 |
| Windows Server licensing + antivirus + monitoring | $3,800 |
| Power, facilities, server-room allocation | $6,700 |
| Backup (media, offsite storage, software maintenance) | $5,400 |
| YAT ICT staff (admin 0.20 FTE + incident 0.05 FTE) | $27,500 |
| Total recurring per year | $73,400 |

# Appendix 2 — LMS Market Evaluation (summary)

Candidate replacement platforms were scored against the §5.1 requirements. DOODLE was selected on the balance of functional fit, total cost of ownership, RTO-sector fit, accessibility conformance, and vendor longevity.

| Criterion | DOODLE (selected) | Alternative 1 | Alternative 2 |
| --- | --- | --- | --- |
| Functional fit to YAT requirements | Strong | Strong | Moderate |
| On-prem deployment supported | Yes | Yes | SaaS only |
| WCAG 2.1 AA conformance | Yes | Partial | Yes |
| AD / O365 / AVETMISS integration | Yes | Yes | Limited |
| 5-year total cost of ownership | Competitive | Higher | Lower (but SaaS — out of scope) |
| Vendor longevity & roadmap | Strong | Moderate | Strong |